|  |  |  |
| --- | --- | --- |
| **Targets:** * Encourage more walking, cycling, bus use….
* Reduce the number of journeys to school by car by 1%
* Develop program of Road safety and environmental awareness education
* Establish an ongoing strategy towards school travel
 | **Leaders: Corinne Singh, John Hastings****Link Governors: Vicky Maunder** | **Task/Action needed:**Survey completed in Autumn term to update baseline travel information (December 2015) Survey completed in Spring term to update progress (February 2016)3 consultations put in place: neighbours, parents and school community, school councilJRSOs to talk about Road Safety in whole school assembly.Walk to School Week in Autumn and Spring Term to encourage walking, cycling, bus use etcPromote the school Travel Plan through Newsletters and school website.Road Safety and Travel Plan initiatives displayed on school Notice Board and shared with Governors.JRSOs to introduce a Walk to School 100 word writing competition. (February)Road Safety/Travel in our school curriculumBikeability for Years 5 and 6 (Summer Term)Scooter Training for KS1 (Summer Term)Use of Public Transport on school trips encouragedTravel Plan display board showing initiativesDr Bike (Summer Term) |
| **Resources****Finance: £200** |
| **Timescale: June 2016** |
|  |
| **Monitoring/Evaluation:*** travel plan reviewed and updated every half term.
 | **How will we know if we’ve been successful:*** Percentage of children walking to school increased
* Number of journeys to school by car reduced from 14% to 6%
* All pupils receive Road Safety Education
* School Travel Strategy in place, monitored regularly and effective
 |